Objective 3 — Analysis Plan

Attention-Based Interpretability Layer for

Drug–Target Interaction Prediction

H-GNN-RNN-DTI  |  USM  |  Assoc. Prof. Dr. Nurul Hashimah

2026

0. Objective Statement and Research Question

Objective 3 — To implement and benchmark an attention-based interpretability layer that demonstrates the model's ability to generate both quantitative and visual explanations of DTI/DTA predictions. This will create an actionable tool for guiding structure–activity relationship (SAR) studies and providing chemically and biologically meaningful rationales for model decisions.

RQ3: Can the attention-enhanced H-GNN-RNN-DTI model generate interpretable, biologically meaningful insights into drug–target interactions that are consistent with known binding mechanisms?

Scope and Deliverables

This objective has three components mirroring the proposal §3.7: (1) Attention-Based Attribution — extract and analyse cross-attention weights from the Gated Cross-Attention module to attribute predictions to individual drug atoms and protein residues; (2) Visualization — produce heatmaps, molecular highlight plots, and graph-based Grad-CAM maps; (3) Case Study Validation — compare model-predicted binding hotspots against experimentally validated binding sites from the Protein Data Bank (PDB).

| Component | Proposal Section | Key Output |
| --- | --- | --- |
| 3.1 Attribution Extraction | §3.7.1 | Per-atom and per-residue importance scores |
| 3.2 Graph Grad-CAM | §3.7.1 | Gradient-weighted node importance (drug GNN) |
| 3.3 Visualization | §3.7.2 | Molecule highlight plots + sequence heatmaps |
| 3.4 Quantitative Metrics | §3.7 (implied) | Faithfulness, consistency, specificity scores |
| 3.5 Case Study Validation | §3.7.3 | PDB-verified binding hotspot overlap report |
| 3.6 Reporting | Expected Outcome §3 | Interpretability section in paper |

Model Configuration

All interpretability experiments run on the C3 configuration (ESM-2 150M + 1:5 ratio + BindingDB pretraining) — the best overall AUROC model from Objective 2. The best seed checkpoint from each dataset/split is used for attribution analysis.

| Setting | Value |
| --- | --- |
| Embedding | ESM-2 150M (480-dim → projected to 320 inside model) |
| Negative ratio | 1:5 |
| Pretraining | BindingDB 49,499 pairs (pretrain epoch 42) |
| Primary datasets | luo_17 (cold_target best), yamanishi_e (all 4 splits) |
| Secondary dataset | davis (DTA — for affinity regression interpretability) |
| Seeds analysed | Best seed per split (checkpoint with highest val AUROC) |

Phase 1 — Attention Weight Extraction

The Gated Cross-Attention module in model/fusion.py computes bidirectional cross-attention between drug atom embeddings and protein residue embeddings. This phase instruments the module to capture and return these attention weight matrices for any drug–target pair.

Step 1.1 — Instrument GatedCrossAttention

File to modify: model/fusion.py — GatedCrossAttention.forward(). Currently the module discards attention weights after the gating step. Add a return_weights=False argument; when True, return (output, attn_d2p, attn_p2d).

Implementation Details

Shape:  Drug→Protein attention (attn_d2p): shape (B, N_atoms, L_residues) — each row is a drug atom's attention distribution over protein residues.

Shape:  Protein→Drug attention (attn_p2d): shape (B, L_residues, N_atoms) — each row is a residue's attention over drug atoms.

Heads:  Multi-head attention: average across heads before storing, or store all heads and aggregate downstream.

Gate:  Gating weights (g_d, g_p) from the sigmoid gate also capture cross-modal information flow — optionally store these as secondary attribution signals.

Code Sketch

def forward(self, drug_emb, prot_emb, return_weights=False):
    # ... existing cross-attention computation ...
    attn_d2p = F.softmax(scores_d2p / math.sqrt(d_k), dim=-1)  # (B, N, L)
    attn_p2d = F.softmax(scores_p2d / math.sqrt(d_k), dim=-1)  # (B, L, N)
    if return_weights:
        return fused_repr, attn_d2p.detach(), attn_p2d.detach()
    return fused_repr

Step 1.2 — Inference Attribution Pipeline

Create a new script: interpret/extract_attention.py. This loads a trained checkpoint, accepts a (drug_smiles, protein_sequence) pair, runs a forward pass with return_weights=True, and returns atom-level and residue-level raw attention scores.

○  Create interpret/ directory with __init__.py

○  Script: interpret/extract_attention.py — load checkpoint, build graph, run inference, return weights

○  Output: attention_weights.npz — arrays attn_d2p (N_atoms × L_residues), attn_p2d (L_residues × N_atoms), prediction score

○  Support both DTI (binary logit) and DTA (affinity scalar) task heads

Atom Importance Score (Drug)

Aggregate the drug atom's column in attn_p2d (how much each protein residue attends to each drug atom) and average over residue positions: atom_importance[i] = mean over j of attn_p2d[j,i]. Alternatively use max-pooling for sparse attribution. Normalize to [0, 1].

Residue Importance Score (Protein)

Aggregate the protein residue's row in attn_d2p (how much each drug atom attends to each residue) and average over atom positions: residue_importance[j] = mean over i of attn_d2p[i,j]. Normalize to [0, 1].

Step 1.3 — Sanity Checks and Validation

Before running downstream analyses, verify: (a) attention weights are non-uniform (not flat 1/N), (b) high-confidence correct predictions have higher peak attribution than low-confidence or wrong predictions, (c) permuting input atoms changes the atom scores (input-sensitivity check).

| Check | Method | Pass Criterion |
| --- | --- | --- |
| Non-uniformity | Compute entropy of attn_d2p rows; compare to max-entropy uniform baseline | Mean entropy < 0.8 × log(L) |
| Input sensitivity | Permute atom order; check that atom scores permute consistently | Spearman ρ > 0.8 before/after reordering |
| Prediction coherence | Rank pairs by prediction confidence; compare mean peak attribution | Higher confidence → higher peak score |
| Gradient consistency | Compare attention attribution vs. simple gradient norm at input | Pearson r > 0.5 on held-out set |

Phase 2 — Graph Grad-CAM Implementation

Attention weights reflect the model's routing of information but are not directly tied to the prediction output. Gradient-weighted Class Activation Mapping (Grad-CAM) addresses this by computing the gradient of the prediction score w.r.t. the intermediate node embeddings, giving a saliency measure grounded in the loss landscape.

Reference: Grad-CAM for GNNs — GNNExplainer (Ying et al. 2019) and graph-Grad-CAM variants. Proposal §3.7 explicitly lists 'graph-based variant of Grad-CAM' as the visualization method.

Step 2.1 — Drug Graph Grad-CAM

Algorithm

1.  Forward pass through DrugEncoder; capture node embeddings at each GAT layer (register forward hooks on all 3 GAT conv layers).

2.  Compute prediction score (DTI logit or DTA affinity). Backpropagate to obtain gradients at each layer's node embeddings.

3.  Grad-CAM score per node: cam[i] = ReLU( mean_over_channels(grad[i] * activation[i]) ). Use the last GAT layer embeddings.

4.  Normalize to [0,1] across all atoms in the molecule.

5.  Compare with attention-based atom importance: do the two methods agree on which atoms matter?

Implementation

○  Create interpret/grad_cam.py — register hooks, compute gradients, return per-node scores

○  Requires model.eval() but with gradient tracking: use torch.enable_grad() in inference

○  Handle batched inference carefully — compute per-sample Grad-CAM, not batch-averaged

Step 2.2 — Protein Residue Grad-CAM

The ProteinEncoder outputs per-residue embeddings (after BiGRU) before attention pooling. Compute gradients of the prediction w.r.t. these per-residue hidden states to get residue saliency scores. This complements the cross-attention residue importance from Phase 1.

○  Hook the BiGRU hidden state output (before attention pooling) in ProteinEncoder

○  Compute gradient norm per residue position → residue_saliency[j] = ||grad_h[j]||_2

○  Normalize and compare against cross-attention residue_importance[j]

Step 2.3 — Ensemble Attribution

Combine the two attribution signals for each modality into an ensemble score: atom_ensemble = alpha * attn_importance + (1-alpha) * gradcam_score, where alpha=0.5 by default. Report both individual and ensemble scores in the paper.

| Attribution Method | Drug Atoms | Protein Residues | Grounded in Prediction? |
| --- | --- | --- | --- |
| Cross-attention (Phase 1) | Yes (attn_p2d column sum) | Yes (attn_d2p row sum) | Indirectly |
| Grad-CAM (Phase 2) | Yes (GAT layer grad) | Yes (BiGRU hidden grad) | Directly |
| Ensemble (alpha=0.5) | Yes | Yes | Combined |

Phase 3 — Visualization Module

Visualizations are the primary output of the interpretability framework — they make attribution scores communicable to chemists and biologists without domain ML knowledge. Three plot types are required: (1) molecular atom coloring, (2) protein sequence heatmap, and (3) cross-attention interaction matrix.

Step 3.1 — Drug Molecule Highlight Plot

Use RDKit's drawing utilities to produce a 2D molecular structure diagram where each atom is colored by its ensemble attribution score. High-importance atoms appear red/orange; low-importance atoms appear grey/white.

Implementation

○  Script: interpret/visualize_drug.py

○  Use rdkit.Chem.Draw.rdMolDraw2D with atom highlight colors from a matplotlib colormap (e.g., RdYlGn_r)

○  Overlay atom importance scores as a continuous color scale; include colorbar in figure

○  Save as PNG (300 dpi) and SVG for paper inclusion

○  Also produce a table of top-5 atoms by importance: atom index, element, importance score, SMARTS substructure match

Functional Group Annotation

After ranking atoms by importance, map high-importance clusters to known pharmacophoric groups (hydrogen bond donors/acceptors, hydrophobic regions, aromatic rings, charged groups) using RDKit's GetSubstructMatches with SMARTS patterns. Report which pharmacophore types the model consistently attends to across multiple drug-target pairs.

Step 3.2 — Protein Sequence Heatmap

Visualize residue importance as a 1D heatmap aligned to the protein sequence. Annotate known functional regions (active site, binding pocket) if available from UniProt annotations.

Implementation

○  Script: interpret/visualize_protein.py

○  Plot residue_importance as a bar chart or 1D heatmap using seaborn/matplotlib

○  Color scale: white (unimportant) → deep blue (highly important)

○  Annotate x-axis with secondary structure elements if available (helix/sheet/loop from PDB DSSP)

○  For luo_17 targets, cross-reference UniProt binding site annotations (BioMart / UniProt REST API)

Step 3.3 — Drug-Protein Cross-Attention Matrix

Visualize the full attn_d2p matrix (N_atoms × L_residues) as a 2D heatmap. This reveals which drug atoms interact with which protein regions, exposing the learned binding interface.

○  Script: interpret/visualize_cross_attention.py

○  Use seaborn.heatmap with atom SMILES labels on y-axis and residue indices on x-axis

○  Downsample long sequences (>512 residues) by max-pooling over 5-residue windows

○  Highlight rows/columns that exceed 2× mean attention (putative binding contacts)

Step 3.4 — Batch Visualization Pipeline

For the paper, select 3–5 representative drug-target pairs per dataset and generate all three plot types for each. Automate via a master script that calls the three visualize_*.py scripts for each pair.

○  Script: interpret/run_visualization.py — loop over selected pairs, call all three scripts, output to paper/figures/interpretability/

○  Pair selection criteria: correct predictions with highest confidence, covering diverse chemical scaffolds

Phase 4 — Quantitative Interpretability Metrics

Qualitative visualizations must be supported by quantitative metrics that can be reported in a table. Three metric families are proposed: faithfulness (does masking important atoms hurt the prediction?), consistency (do the same atoms/residues get high scores across seeds?), and specificity (are the attributed features chemically/biologically meaningful?).

Step 4.1 — Faithfulness: Atom Masking Experiment

Mask the top-K% highest-importance atoms in the drug graph by zeroing their node features. Measure the drop in prediction confidence. If the attribution is faithful, masking important atoms should cause a larger drop than masking random atoms.

Protocol

| K% | Expected Outcome (faithful model) |
| --- | --- |
| Top 10% atoms masked | Prediction confidence drops by >20% on average |
| Top 25% atoms masked | Prediction confidence drops by >40% on average |
| Random 10% atoms masked (control) | Smaller drop than Top 10% |
| Random 25% atoms masked (control) | Smaller drop than Top 25% |

Metric: Faithfulness Score = AUC of the confidence-drop vs. K% curve. Higher score = more faithful attribution. Report for both attention and Grad-CAM methods.

○  Script: interpret/faithfulness.py — systematic masking experiment over 100 drug-target pairs per dataset

○  Report mean ± std of faithfulness score for each attribution method (attention, Grad-CAM, ensemble)

Step 4.2 — Consistency: Cross-Seed Agreement

For each drug-target pair, run attribution extraction using checkpoints from all 5 seeds. Compute Spearman rank correlation between the atom importance vectors from different seeds. High consistency = the attribution is a stable model property, not a training-run artifact.

○  Run extract_attention.py for all 5 seeds on 20 representative pairs per split

○  Compute pairwise Spearman ρ between seed pairs → report mean ± std for each dataset/split

○  Flag pairs where consistency < 0.5 as potentially unreliable

Step 4.3 — Specificity: Pharmacophore Alignment Score

Quantify whether high-importance atoms correspond to known pharmacophoric features. Use RDKit's pharmacophore detection (GetPharmacophoreDescriptors or SMARTS matching) to label each atom as pharmacophoric or not. Compute precision@K: of the top-K atoms by importance, what fraction are pharmacophoric?

| Metric | Description | Target Value |
| --- | --- | --- |
| Pharmacophore Precision@5 | % of top-5 atoms matching known pharmacophores | > 60% |
| Binding Pocket Recall | % of known binding-pocket residues in top-25% residue scores | > 50% |
| Consistency ρ (cross-seed) | Mean Spearman ρ between seed pairs | > 0.7 |
| Faithfulness AUC | AUC of confidence-drop vs. K% curve | > 0.6 |

Phase 5 — Case Study Validation

The proposal §3.7.3 requires validating predicted binding hotspots against experimentally validated binding sites from crystal structures in the PDB. This phase selects well-characterised drug-target pairs, retrieves PDB structures, annotates binding sites, and computes overlap between model attribution and experimental binding residues.

Step 5.1 — Case Study Pair Selection

Selection Criteria

The drug-target pair must be present in luo_17 or yamanishi_e (or davis for DTA).

The model must predict the pair correctly (true positive) with high confidence (top 10% by predicted probability).

A PDB crystal structure of the complex must exist (drug bound to target protein).

The pair should cover diverse chemical scaffolds — aim for at least one kinase inhibitor, one GPCR ligand, and one enzyme inhibitor.

Candidate Pairs from luo_17 (DrugBank dataset)

luo_17 uses DrugBank IDs and UniProt targets. Query PDB for co-crystal structures using the PDB REST API (search by UniProt accession + small molecule ligand). Target 5–8 pairs total across both datasets.

○  Script: interpret/select_case_studies.py — query PDB REST API, filter by model confidence, output candidate list

○  Manual review: confirm ligand in crystal matches the drug SMILES in dataset

| Dataset | Target Type | Example Pairs (illustrative) |
| --- | --- | --- |
| luo_17 | Kinase (DrugBank) | Imatinib/ABL1, Erlotinib/EGFR — confirmed co-crystals in PDB |
| luo_17 | GPCR (DrugBank) | Risperidone/DRD2 or similar — check PDB 6CM4 etc. |
| yamanishi_e | Enzyme (Enzymes subset) | Acetaminophen/COX-1 analog — verify SMILES match |
| davis | Kinase (DTA) | Staurosporine/PKCα — broad-spectrum binding for affinity case |

Step 5.2 — PDB Binding Site Annotation

For each selected pair, extract the binding site residues from the PDB structure: residues within 4 Å of any ligand heavy atom. This gives the ground-truth set of binding residues.

○  Use Biopython (Bio.PDB) to parse PDB structure and extract residues within 4 Å of ligand

○  Map PDB residue indices to protein sequence indices (handle insertions/deletions via sequence alignment)

○  Store as: binding_residues = {uniprot_id: set(residue_indices)} for each case study target

Step 5.3 — Quantitative Overlap Evaluation

Compare the model's top-K% residues by importance score against the PDB binding residues. Compute precision, recall, and F1 at multiple K thresholds.

| Metric | Formula | Interpretation |
| --- | --- | --- |
| Precision@K% | TP / (TP + FP) where TP = top-K% ∩ binding residues | Are high-importance residues in the binding site? |
| Recall@K% | TP / ¦binding residues¦ | What fraction of binding residues are captured? |
| F1@K% | 2 × P × R / (P + R) | Balance between precision and recall |
| AUROC (residue) | ROC curve treating binding residue as positive class | Overall discriminative power of attribution |

Report results at K=10%, K=25%, K=50% and the full AUROC. Target: mean Precision@25% > 0.5 and Recall@50% > 0.6 across case studies.

○  Script: interpret/evaluate_case_studies.py — compute all metrics for each pair, save to paper/case_study_results.csv

○  Statistical test: is the model attribution significantly better than random at each K threshold (paired t-test vs. uniform baseline)?

Step 5.4 — Qualitative Write-up

For each case study pair, write a 1–2 paragraph analysis including: (a) the predicted interaction class/affinity, (b) the top-5 drug atoms and their functional group identity, (c) the top-10 protein residues and whether they match the PDB binding site, (d) comparison against the crystal structure image (if publishable). These form the qualitative component of Section 3.7.3 in the paper.

○  Prepare 3–5 case study write-ups for the interpretability section of the thesis/paper

○  Include: molecular structure with atom highlighting, sequence heatmap, overlap summary table

Phase 6 — Benchmarking Against Baseline Interpretability Methods

To demonstrate that the cross-attention attribution provides genuine insight (not just a plausible-looking map), compare it against two standard baselines: (1) random attribution (lower bound) and (2) integrated gradients at the input feature level.

Step 6.1 — Random Attribution Baseline

Assign uniform random importance scores to atoms and residues. Use 100 random seeds per pair. This sets the floor for all quantitative metrics.

Step 6.2 — Input Gradient Baseline

Compute the gradient of the prediction w.r.t. the raw input atom features (before the GAT). The L2 norm of the gradient at each atom position gives a naive saliency score. This is a model-agnostic baseline that requires no architectural modification.

○  Implement in interpret/input_gradient.py — requires autograd at raw input node features (no hooks needed)

Step 6.3 — Comparison Table

| Method | Requires Architecture Change? | Grounded in Prediction? | Expected Precision@25% |
| --- | --- | --- | --- |
| Random (baseline) | No | No | ~25% (chance) |
| Input gradient | No | Yes | 30–40% (target) |
| Cross-attention (Phase 1) | Yes | Indirectly | 40–55% (target) |
| Grad-CAM (Phase 2) | Yes | Yes | 45–60% (target) |
| Ensemble (Phase 2.3) | Yes | Yes | 50–65% (target) |

If ensemble Precision@25% is < 40%, investigate whether the attribution is model-meaningful or whether the GCA module's attention weights are not strongly informative (flat attention over long protein sequences is a known failure mode).

Phase 7 — Reporting: Paper Section 3.7 and Evaluation Report

All results feed into the paper's interpretability section and into evaluation_report.md Section 3.11 (new section for Objective 3). The goal is a self-contained, reproducible interpretability analysis that can stand alongside the predictive performance results.

Step 7.1 — Evaluation Report Section 3.11

Subsections to Write

3.11.1  Attribution Extraction — describe the cross-attention weight extraction pipeline

3.11.2  Graph Grad-CAM — describe the GNN Grad-CAM implementation

3.11.3  Visualization Gallery — 2–3 key figures (molecule highlight, sequence heatmap, cross-attention matrix)

3.11.4  Quantitative Metrics — faithfulness, consistency, pharmacophore precision tables

3.11.5  Case Study Validation — 3–5 pair analyses with PDB comparison

3.11.6  Baseline Comparison — attribution methods ranked by precision@K

Step 7.2 — Summary Tables for Paper

| Table | Content | Location |
| --- | --- | --- |
| Table 21 | Quantitative interpretability metrics (all attribution methods, both datasets) | Section 3.11.4 |
| Table 22 | Case study binding site overlap results (precision/recall/F1 per pair) | Section 3.11.5 |
| Table 23 | Attribution method comparison (vs. random and input gradient baselines) | Section 3.11.6 |

Step 7.3 — Figures for Paper

| Figure | Description |
| --- | --- |
| Fig. 3.X | Example drug molecule with atom importance coloring (luo_17 case study) |
| Fig. 3.X+1 | Protein sequence heatmap for the same pair — known binding residues annotated |
| Fig. 3.X+2 | Cross-attention matrix (drug atoms × protein residues) — binding interface heatmap |
| Fig. 3.X+3 | PDB crystal structure overlaid with top-10 model-predicted binding residues |
| Fig. 3.X+4 | Faithfulness curve: prediction confidence vs. % atoms masked (all methods) |

Step 7.4 — Commit and Version Control

○  Commit all interpret/ scripts and paper/figures/interpretability/ after each phase

○  Tag the commit with 'obj3-phaseN-complete' for traceability

○  Update evaluation_report.md Section 3.11 incrementally as each phase completes

Execution Timeline and Dependencies

The phases are largely sequential: Phase 1 (extraction) must complete before Phases 2–6. Visualization (Phase 3) and Quantitative Metrics (Phase 4) can run in parallel once attribution scores exist. Case Study Validation (Phase 5) has an external dependency on PDB structure retrieval.

| Phase | Prerequisite | Est. Duration | Key Risk |
| --- | --- | --- | --- |
| Phase 1 — Extraction | C3 checkpoints (done) | 1–2 days | GCA module may not store weights; requires refactoring |
| Phase 2 — Grad-CAM | Phase 1 complete | 1–2 days | Memory: per-sample gradient computation on long proteins |
| Phase 3 — Visualization | Phase 1 or 2 complete | 1–2 days | RDKit version compatibility; SVG export quality |
| Phase 4 — Quant. Metrics | Phase 1 + 2 complete | 2–3 days | Masking experiment is slow (100 pairs × 5 K-values × forward pass) |
| Phase 5 — Case Studies | Phase 3 + PDB retrieval | 3–4 days | PDB API rate limits; sequence alignment errors |
| Phase 6 — Baselines | Phase 1 complete | 1 day | Input gradient baseline may have very different scale |
| Phase 7 — Reporting | Phases 3–6 complete | 2–3 days | Figure quality for publication (DPI, font sizes) |

Critical path: Phase 1 → Phase 2 → Phase 4 → Phase 5 → Phase 7. Total estimated duration: 11–17 working days assuming GPU access for forward passes.

Dependencies and Tools

| Tool / Library | Purpose | Already Installed? |
| --- | --- | --- |
| torch.autograd | Gradient computation for Grad-CAM | Yes (PyTorch) |
| rdkit.Chem.Draw | 2D molecular visualization with atom colors | Yes (RDKit) |
| seaborn / matplotlib | Sequence heatmaps and cross-attention matrix | Yes |
| Bio.PDB (Biopython) | PDB structure parsing and binding site extraction | Check: pip install biopython |
| requests / PDB REST | PDB structure and annotation retrieval | Check: pip install requests |
| scipy.stats | Spearman correlation, paired t-tests | Yes (scipy) |

Expected Outcomes and Success Criteria

Objective 3 is complete when all three components of the proposal §3.7 are delivered: attribution extraction (§3.7.1), visualization (§3.7.2), and case study validation (§3.7.3).

Minimum Viable Outcome

✓  GatedCrossAttention instrumented to return attention weights without degrading prediction performance

✓  Per-atom and per-residue importance scores computed for all selected case study pairs

✓  At least 3 drug molecule highlight plots and 3 protein sequence heatmaps generated

✓  Quantitative faithfulness and consistency metrics computed and reported

✓  At least 3 case study pairs validated against PDB binding sites (Precision@25% > 40%)

✓  Evaluation report Section 3.11 fully written with all tables and figures

Stretch Goals

○  Extend case studies to DAVIS DTA dataset — map affinity-weighted attention to binding free energy contributions

○  3D protein structure visualization: project residue importance onto PDB RCSB 3D viewer (PyMOL script or NGL Viewer)

○  Interactive HTML report: plotly-based interactive cross-attention matrix + molecule viewer

○  Comparison with NHGNN-DTA (He et al. 2023) and MutualDTA (Yuan et al. 2025) — two published interpretable DTI models

Failure Modes and Contingencies

| Risk | Likelihood | Contingency |
| --- | --- | --- |
| Cross-attention is too flat (uniform over residues) | Medium — long proteins dilute attention | Switch to Grad-CAM as primary attribution; report attention as secondary |
| PDB structures not available for dataset pairs | Low–Medium — luo_17 is DrugBank-based | Use AlphaFold2 structures + predicted binding pockets from FPocket |
| Interpretation metrics low (Precision@25% < 35%) | Low — model has strong AUROC so representations are meaningful | Report negative result transparently; analyse why (attention vs. gradient divergence) |
| GPU memory issues with per-sample Grad-CAM | Medium — long protein sequences | Process single samples (batch_size=1), or truncate proteins at 512 residues |

Proposed File Structure

Modeling-DTI/
├── interpret/
│   ├── __init__.py
│   ├── extract_attention.py      # Phase 1: attention weight extraction
│   ├── grad_cam.py               # Phase 2: graph Grad-CAM
│   ├── visualize_drug.py         # Phase 3: atom coloring
│   ├── visualize_protein.py      # Phase 3: residue heatmap
│   ├── visualize_cross_attention.py  # Phase 3: interaction matrix
│   ├── run_visualization.py      # Phase 3: batch pipeline
│   ├── faithfulness.py           # Phase 4: masking experiment
│   ├── consistency.py            # Phase 4: cross-seed agreement
│   ├── pharmacophore_precision.py # Phase 4: specificity
│   ├── select_case_studies.py    # Phase 5: pair selection
│   ├── retrieve_pdb.py           # Phase 5: PDB download + binding site
│   ├── evaluate_case_studies.py  # Phase 5: overlap metrics
│   └── input_gradient.py         # Phase 6: baseline
├── paper/
│   ├── figures/
│   │   └── interpretability/     # All plots from Phase 3
│   ├── case_study_results.csv    # Phase 5 output
│   └── evaluation_report.md      # Section 3.11 added here
└── model/
    └── fusion.py                 # Modified: return_weights argument

All scripts under interpret/ are standalone — they import from model/ and data/ but do not modify training code. The model/fusion.py change is backward-compatible (default return_weights=False).

Summary of Objective 3 vs. Proposal Mapping

| Proposal §3.7 Element | This Plan | Phase |
| --- | --- | --- |
| Attention-Based Attribution — cross-attention weights quantify atom/residue contribution | Phase 1: extract_attention.py — attn_d2p, attn_p2d → importance scores | 1 |
| Graph-based Grad-CAM for molecular substructures | Phase 2: grad_cam.py — GAT layer hooks + gradient × activation | 2 |
| Heatmaps and saliency maps overlaid on molecular graphs / protein sequences | Phase 3: visualize_drug.py, visualize_protein.py, visualize_cross_attention.py | 3 |
| Quantitative attribution metrics (faithfulness, consistency, specificity) | Phase 4: faithfulness.py, consistency.py, pharmacophore_precision.py | 4 |
| Case study validation against PDB crystal structures | Phase 5: select_case_studies.py → retrieve_pdb.py → evaluate_case_studies.py | 5 |
| Baseline comparison to establish attribution quality | Phase 6: input_gradient.py vs. attention vs. Grad-CAM | 6 |
| Paper section on interpretability findings | Phase 7: evaluation_report.md Section 3.11 + figures | 7 |

Objective 3 is the final research objective. On completion, all three research questions (RQ1: fusion architecture, RQ2: cold-start representation, RQ3: interpretability) will have been fully addressed and reported.